## Name of Project
Healthy Body Vitamins |  |  | Coach: Mr. Messer | [13 empty] | Coach: | [5 empty] | Mr. Messer | [5 empty] | G |  | Team #: 3
Project Sponsor: Mr. Messer | [22 empty] | Overall Status | [7 empty] | Updated: | [7 empty] | 2022-07-27
DMAIC Type |  | Major Tasks | 2022-05-24 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 | 2022-07-05 | 2022-07-12 | 2022-07-19 | 2022-07-26 | 2022-08-02 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-30 | 2022-09-06 | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-04 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | John | Caine | Will | Brian
Define |  | Initial Meeting with Project Sponsor | G | C |  |  | Summer Break | [5 empty] | End of Semester | [5 empty] | End of Semester - Exam Week 1 | [12 empty] | R | A | R | R
Define |  | Determine Major Objectives | G | C | [27 empty] | R | A | R | R
Define |  | Understand Internal Timeline | G | C | [27 empty] | A | R | R | R
Define |  | Establish Project Charter | G | C | [27 empty] | R | A | R | R
Define |  | Project Proposal Presentation | G | G | C | [26 empty] | R | A | R | R
Define |  | Finalize assumptions | G | G | C | [26 empty] | R | R | R | A
Measure |  | Develop demand supply model | G | G | G | G |  | C | [23 empty] | R | R | A | R
Measure |  | Develop arena model | G | G | G | G |  | G | G | G | R | C | [19 empty] | R | A | R | R
Measure |  | Develop Blueprints for Warehouse | G | G | G | C | [25 empty] | R | A | R | R
Measure |  | Develop Layout for Warehouse | G | G | G | G |  | G | C | [22 empty] | A | R | R | R
Analyze |  | Process alaysis for employees | G | G | G | G |  | G | G | G | G | S | [19 empty] | A | R | R | R
Analyze |  | Cost analysis for facility | G | G | G | G |  | G | G | G | G | C | [19 empty] | R | R | A | R
Implement |  | Excutive Summary Summary | [7 empty] | G | G | C | [19 empty] | R | R | R | A
Project Proposal Presentation - 6/9/22
Mid-Project Update - 7/722
Project Executive Summary - 7/29/22
Final Project Presentation Slides - Draft - 8/1/22
Final Project Presentation Slides - Final Copy - 8/3/22
Final Presentation - 8/4/22
Deliverables Status
Objective A
Objective B
Objective C
|  |  | Dates | [28 empty] | Name(s)
|  |  | 2022-05-24 | 2022-05-31 | 2022-06-07 | 2022-06-14 | 2022-06-21 | 2022-06-28 | 2022-07-05 | 2022-07-12 | 2022-07-19 | 2022-07-26 | 2022-08-02 | 2022-08-09 | 2022-08-16 | 2022-08-23 | 2022-08-30 | 2022-09-06 | 2022-09-13 | 2022-09-20 | 2022-09-27 | 2022-10-04 | 2022-10-11 | 2022-10-18 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | John | Caine | Will | Brian | 0 | 0 | 0 | 0
Schedule Legend (type the letter in the box to change status) | [7 empty] | Schedule / Duration: | S | On Schedule: |  |  |  | G | [5 empty] | Behind Schedule: | Y |  | R | Responsible |  |  |  |  | C | Consulted
| - Course Requirements | [11 empty] | Will Miss Schedule: | R | [5 empty] | Complete: | C |  | A | Accountable |  |  |  |  | I | Informed
Owners Legend
LSS KPI's
[41 empty] | Projects Savings | Goal | Baseline | Actual
Savings [M $]
[41 empty] | Lean Maturity Index | Goal | Baseline | Actual
Lean Index [%]
[41 empty] | # of Kaizen Events | Goal | Baseline | Actual
K.E. [Units]
[41 empty] | # of Closed Projects | Goal | Baseline | Actual
Projects [Units]
[41 empty] | Bronze Certification | Goal | Baseline | Actual
Bronze Certified [%]
[41 empty] | DL Shop Floor Cert | Goal | Baseline | Actual
DL's Certified [%]
Formulas:
C = [Coach: Mr. Messer]+7
C = [C]+7
G = [C]+7
G = [G]+7
Summer Break = [G]+7
R = [G]+7
End of Semester = [C]+7
Note on AE2: Overall Status: Highlight the overall status of the X-Matrix based on the status of the Major Tasks.
Note on D4: Major Tasks: Include all project tasks & input in DMAIC order (i.e., all Define tasks before Measure tasks, etc.).